## Title
Assignment | Earned Value analysis
Full Name | Nidhi Gupta
Student ID | 100910487
E mail | nidhi.gupta@georgebrown.ca
Date | April 4th,2024

## Ques 1
[8 empty] | Activity | Starting Date | End Date | Pesimistic Duration | Optimistic Duration | Most Likely Duration | Weighted Average
Ques 1 | [7 empty] | A | 1 | 3 | 6 | 2 | 4 | 4
[8 empty] | B | 2 | 3 | 12 | 4 | 5 | 6
[8 empty] | C | 3 | 4 | 15 | 3 | 6 | 7
[8 empty] | D | 3 | 5 | 12 | 4 | 5 | 6
[8 empty] | E | 3 | 6 | 13 | 3 | 5 | 6
|  |  | C=7 |  |  | F=9 |  | F | 4 | 7 | 20 | 2 | 8 | 9
[8 empty] | G | 5 | 7 | 15 | 5 | 7 | 8
[8 empty] | H | 6 | 8 | 14 | 2 | 8 | 8
[8 empty] | I | 8 | 7 | 13 | 1 | 4 | 5
A=4
G=8
|  |  |  | D=6 |  |  |  | Critical Path | BEHI=25
| B=6 | [6 empty] | Activity | ES | EF
[8 empty] | A | 1 | 4
|  |  |  | E=6 |  |  | I=5 | B | 1 | 6
[8 empty] | C | 7 | 13
[8 empty] | D | 7 | 12
[8 empty] | E | 7 | 12
[5 empty] | H=8 |  |  | F | 14 | 22
[8 empty] | G | 13 | 20
[8 empty] | H | 13 | 20
[8 empty] | I | 21 | 25
1
2
8
7
3
4
5
6

## Ques 2
Ques 2
A) | Total PV | 2500
B) | Total EV | 3180
C) | Total AC | 2825
D) | CPI | 1.125
| SPI | 1.272
E) | Estimate at completion | 4575
F) | Forecasted Duration | 19.6 days

## Rough Sheet Question 2
Activity | Budget | Actual Cost | Status | ES | EF | Pv | EV
A | 400 | 600 | 100% | 1 | 4 | 400 | 400
B | 200 | 150 | 100% | 1 | 6 | 200 | 200
C | 300 | 350 | 100% | 7 | 13 | 300 | 300
D | 600 | 525 | 100% | 7 | 12 | 600 | 600
E | 450 | 450 | 100% | 7 | 12 | 450 | 450 |  |  |  | EAC
F | 900 | 450 | 70% | 14 | 22 | 100 | 630
G | 1000 | 300 | 60% | 13 | 20 | 250 | 600
H | 800 |  |  | 13 | 20 | 200 |  | SPI | EV/PV | 1.272 | F | 19.6541
I | 500 |  |  | 21 | 25 | 0 |  | CPI | EV/AC | 1.1257
| 5150 | 2825 |  |  |  | 2500 | 3180
| Estimate at completion | 4575.0786