## Risk Log
Risk No | Risk Description | Category | Probability | Impact | Risk Score | Response | Mitigation Strategy
1 | Unidentified Stakeholder: Stakeholders identities and roles are not identified within the project. | Other | 3-Medium | 4 - High | 12 | Control | Identify all of the stakeholders involved in our project and learn about their concerns by doing a thorough stakeholder analysis.
2 | Inadequade project scope: Lack of clarity in defining the project scope | Scope | 3-Medium | 5-Very High | 15 | Avoid | Identify deliverables, features, requirements, and essential activities.
3 | Time Constraints: Limitation on the amount of time available to complete the task or project | Schedule | 3 - Medium | 4 - High | 12 | Control | Prioritize tasks, allocate resources efficiently, and streamline processes to meet deadlines.
4 | Budget Constraints: Restriction or limitation on the financial resources allocated for a project | Cost | 3 - Medium | 3 - Medium | 9 | Accept | Prioritize project expenditures and explore cost-saving measures without compromising quality.
5 | Scope Creep: expansion of project scope beyond its original boundaries. | Scope | 4 - High | 5 - Very High | 20 | Avoid | Clearly define project scope, set boundaries, and implement change management processes to control scope creep.
6 | Inadequate Team Collaboration: It can hinder productivity, creativity, and overall team performance. | Collaboration | 3 - Medium | 4 - High | 12 | Control | Create a culture of cooperation among the team, define roles and duties, and provide efficient routes of communication.
7 | Insufficient Technical Expertise: Team does not have necessary skills and knowledge to do a particular task. | Knowledge / Skills / Experience | 3 - Medium | 3 - Medium | 9 | Accept | Invest in training and development opportunities for team members, and consider outsourcing technical tasks if necessary.
8 | Content Inaccuracy: Unreliable or inaccurate information. | Knowledge / Skills / Experience | 3 - Medium | 5 - Very High | 15 | Avoid | Conduct extensive research and fact-checking to ensure the accuracy of content. Review content with subject matter experts.
9 | Equipment Failure: Equipment is working as intended to. | Hardware | 1 - Very Low | 1 - Very Low | 1 | Investigate | Regularly maintain and update editing equipment. Have technical support available for troubleshooting.
10 | Members Leaving: Team Members leaving the project because of unforseen circumstances. | Collaboration | 1 - Very Low | 3-Medium | 3 | Accept | Build trust through transparency, reliability, and consistent engagement.
11 | Improper risk management: Increasing vulnerability to unforeseen threats | Other | 3-Medium | 4-High | 12 | Control | Adequate training and education, and assigning clear roles and responsibilities.
12 | Stakeholder Availibilty: Unexpected Changes in Stakeholder Availability | Other | 3 - Medium | 4 - High | 12 | Control | Develop contingency plans for rescheduling meetings or adjusting project timelines.
13 | Stakeholder Expectation: Misalignment with Stakeholder Expectations | Other | 3 - Medium | 4 - High | 12 | Control | Regularly communicate project goals and progress to ensure alignment with stakeholder expectations.
14 | Technical Issues: Technical issues with Project software tools | Technological | 1 - Very Low | 1 - Very Low | 1 | Investigate | Regular software maintenance and identifying or fixing any potential issues.
15 | Backup Plan: Lack of Backup Plan for Key Personnel | Knowledge / Skills / Experience | 3 - Medium | 3 - Medium | 9 | Accept | Cross-train team members, identify backups for critical roles, and document key processes and responsibilities.
16 | Scheduling Conflicts: Decisions about which event or task to priortize | Operational | 3 - Medium | 4 - High | 12 | Control | Establish clear communication channels and scheduling protocols to minimize conflicts.
17 | Communication Preferences: Stakeholders' communication preferences not considered | Communication | 2-Low | 3-Medium | 6 | Accept | Respect stakeholders' communication preferences and adapt engagement strategies accordingly.
18 | External Issues: Lack of Contingency Plan for External Dependencies | Operational | 2 - Low | 2 - Low | 4 | Transfer | Identify critical external dependencies, develop contingency plans, and maintain open communication with external partners.
19 | Technical Glitch: Connectivity Issues during Presentation | Technological | 1 - Very Low | 1 - Very Low | 1 | Investigate | Test internet connectivity and have backup plans in place, such as offline presentation options.
20 | Stakeholder Feedback: Inadequate understanding of stakeholders feedback | Other | 3 - Medium | 4 - High | 12 | Control | Proactively seek feedback from stakeholders through surveys, focus groups, or one-on-one meetings.

## Sheet2
Cost | 5 - Very High | 5 - Very High | Avoid
Schedule | 4 - High | 4 - High | Control
Technological | 3 - Medium | 3 - Medium | Accept
Operational | 2 - Low | 2 - Low | Transfer
External | 1 - Very Low | 1 - Very Low | Investigate
Hardware
Scope
Knowledge / Skills / Experience
Project Management
Collaboration
Other